# Repton Parish Council Action Plan 2022 23

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **Aim** | **Objectives** | **Actions** | **Start Date (actual or planned)** | **Completion Date (actual or planned)** |
| Install water monitor on the brook | To ensure that any rise in the levels of the brook are alerted to the flood warden group to ensure their action plan is implemented when needed | * Gain quotes for monitor
* Council agreement for work to be awarded
* Installation of monitor
* Monitor alerts to be tested
 | April 2022 | October 2022 |
| Set up Speed Watch group | To tackle speeding issues in the parish | * Find volunteers to set up community speed watch group
* Group members trained by Derbyshire Police Force
* Radar gun, signs and protective equipment procured
* Identify new speed watch locations
 | October 2021 | December 2022 |
| Install new street light in Matthew’s jitty | To provide light on a well-used public footpath to ensure safety of users | * Gain quote from Derbyshire County Council for purchase and install of light
* Gain permission from land owner/s to install light on their property
* Gain unmetered connection agreement from Western Power Distribution
* Find supplier/s of unmetered electricity provider
* Installation of light to be instructed once all permissions have been gained
 | November 2021 | October 2022 |
| Install of multi-wheeled track | To provide an area for children of the parish and visiting children for outdoor recreation | * Gain support of parishioners
* Identify site of track
* Gain agreement of land owner
* Gain quotes for installation
* Apply for grant funding
* Apply for pre-planning
* Apply for planning permission
* Council agreement for work to be instructed
* Installation of equipment
* Risk assessment for use of equipment
* Maintenance plan of equipment
* Equipment inspection plan
 | April 2022 | December 2023 |
| Tree work | To ensure that trees on parish council land are maintained safely as per insurance | * Gain quotes for a tree survey
* Council agreement for work to be instructed
* Tree inspection course to be attended by Councillor/s
* Work to be completed
* maintenance plan for ongoing inspections
 | June 2021 | October 2022 |
| Burial Ground appearance | To ensure that the burial ground is maintained to a high standard | * Identify areas that need attention
* Gain quotes from the grounds maintenance contractor
* Council to authorise work
* Work to be completed
* Ensure ongoing maintenance plan is in place
 | April 2022 | October 2022 |
| Elderly housing | To ensure that there is adequate provision for housing of the elderly | * Work with County Council, District Council and housing association to ensure that adequate provision is re-instated on the site of the Dales on Askew Grove/Fisher Close in Repton
 | 2020 | Ongoing until housing is available |
| Waste bin provision | To ensure adequate provision of litter and dog waste bins in the parish | * Ensure financial provision in budget
* Identify sites for installation
* Ask District Council for quotes for installation and collection of refuse
* Council to authorise work
* Bin to be installed
 | November 2021 | October 2022 |
| Use of Milton telephone kiosk | Following the purchase of the telephone kiosk in Milton the Council need to identify what they wish it to be used for | * Council to discuss and agree use of telephone kiosk
* Following agreement, action plan to be documented
 | August 2021 | February 2023 |
| Memorial provision | To identify ways in which people of the parish can be remembered via a memorial | * Ideas to be sought on how this can be achieved
* Quotes to be sought
* Policy to be created and agreed
* Advertisement of proposed memorials
 |  |  |
| Queens Platinum Jubilee commemoration | To provide a lasting commemoration to the event | * Identify ways to commemorate
* Gain quotes
* Council to agree work
* Installation of memorial
 | April 2022 | July 2022 |
| Broomhills pavilion | To improve the pavilion building to allow increased benefits of usage | * Discuss ideas with South Derbyshire District Council as part owners of the pavilion
* Instruct survey of building to identify improvements
* Provide District Council with a copy of the survey results
* Meet with District Council to discuss plans
* Document action plan including funding
 | January 2022 | 2024? |

**Plan Review**

This plan will be reviewed at least annually and agreement gained by the Council.

|  |  |  |  |
| --- | --- | --- | --- |
| **Version Number** | **Date of Review** | **Revisions Made** | **Date of Next Review** |
| 1 | October 2022 meeting | Agreed plan | At least one year after adoption or as often as needed |